## Gantt Chart
William Briggs PhD				11%

		09 May 2018

									01					02					03					04					05					06					07					08					09					10					11					12					13					14					15					16					17					18					19					20					21					22					23					24					25					26
Task Names	Resource Names	Start	Duration	Finish	% Complete	Calendar days	Days Completed	Days Remaining	Jan-18					Feb-18					Mar-18					Apr-18					May-18					Jun-18
		01-Jan-2018	990	15-Oct-2021	11%	1384			01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30
Other Tasks	Other Tasks	01-Jun-2018	71	09-Sep-2018	0%	101	0	19
Complete ethics course		01-Jun-2018	9	05-Jun-2018	0%	5	0	9
Attend 2018 CLEF		05-Sep-2018	10	09-Sep-2018	0%	5	0	10
Stopping Methods	Stopping Methods	01-Jan-2018	43	28-Feb-2018	57%	59	98	74
Investigate existing methods to stopping		01-Jan-2018	21	29-Jan-2018	100%	29	21	0
Implement Curve fitting for stopping		01-Jan-2018	43	28-Feb-2018	100%	59	43	0
Implement GP fitting for stopping		01-Jan-2018	43	28-Feb-2018	50%	59	21	22
Evaulation of stopping methods		01-Jan-2018	65	30-Mar-2018	20%	89	13	52
Investigate new methods for stopping		29-Apr-2018	45	01-Jul-2018	5%	64	2	43
Pubmed Protocol Query	Pubmed Protocol	01-Apr-2018	9	12-Apr-2018	42%	12	85	101
Download pubmed and pre process/store index		01-Apr-2018	3	04-Apr-2018	100%	4	3	0
Learn Apache Lucene		05-Apr-2018	4	10-Apr-2018	100%	6	4	0
Learn Rake		10-Apr-2018	3	12-Apr-2018	100%	3	3	0
Extract releavent information from protocol with Rake		11-Apr-2018	8	20-Apr-2018	100%	10	8	0
Create API to query with Rake key word content		11-Apr-2018	9	23-Apr-2018	100%	13	9	0
Run Training topics through IR system		23-Apr-2018	6	30-Apr-2018	100%	8	6	0
Run Test samples through IR system		23-Apr-2018	10	06-May-2018	0%	14	0	10
Evaulate system using trec-eval		23-Apr-2018	10	06-May-2018	80%	14	8	2
Submit for CLEF 2018 Task		06-May-2018	0	06-May-2018	0%	1	0	0
Write up for CLEF 2018 Task		06-May-2018	44	05-Jul-2018	0%	61	0	44
Investigate impact of phrase IR system		05-Jul-2018	45	05-Sep-2018	0%	63	0	45
Text Classifaction	Text Classifaction	01-Apr-2018	88	01-Aug-2018	9%	123	22	220
Text Classifaction of Systematic Reviews		01-Apr-2018	45	01-Jun-2018	0%	62	0	45
Investigate fesaiblity of Task		01-Apr-2018	45	01-Jun-2018	40%	62	18	27
Retreive relevant documents for training		01-Apr-2018	45	01-Jun-2018	10%	62	4	41
Investigate different classifaciton methods		10-Jun-2018	38	01-Aug-2018	0%	53	0	38
Classifical Approaches		10-Jun-2018	38	01-Aug-2018	0%	53	0	38
Deep Learning Approaches		20-Jun-2018	31	01-Aug-2018	0%	43	0	31
Viva	Viva	05-Oct-2020	270	15-Oct-2021	0%	376	0	810
Viva Preperation		05-Oct-2020	270	15-Oct-2021	0%	376	0	270
Writeup		05-Oct-2020	270	15-Oct-2021	0%	376	0	270
Review		05-Oct-2020	270	15-Oct-2021	0%	376	0	270

	Holidays